## Sprint Backlog
PB Name | Task Name | Description and details | Check Out | Status | Remaining Effort [hr]
Product Backlog | Add data validation | Data validation for status and name | Frank | OK | 0
Sprint Backlog | Include task name |  | Frank | Doing | 0
Sprint Backlog | Add data validation | Data validation for person working on it, status and Product Backlog activity | Mary | Done | 0
Sprint Backlog | Track daily progress | Track remaining effort for each task |  | To Do | 4
Visual Progress | Burndown Chart | Show the remaining effort for each day and a trend to evaluate the possibility of success | Daniel | Done | 0
Visual Progress | SCRUM Board | Show the status of each feature | Daniel | Doing | 2
Product Backlog | Crate a master | Create a master with name, description and status | Frank | OK | 3
Collaborative | Use a collaborative platform | Survey if Google Spreadsheets is OK | Mary | To Do | 5

## Burndown Chart
Date | 2021-11-30 | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-05 | 2021-12-06 | 2021-12-07 | 2021-12-08 | 2021-12-09 | 2021-12-10 | 2021-12-11 | 2021-12-12 | 2021-12-13 | 2021-12-14 | 2021-12-15 | 2021-12-16 | 2021-12-17 | 2021-12-18 | 2021-12-19 | 2021-12-20
Day | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Real | 47 | 45 | 44 | 41 | 33 | 42 | 40 | 34 | 33 | 28 | 29 | 14
Plan | 47 | 44.65 | 42.3 | 39.95 | 37.6 | 35.25 | 32.9 | 30.55 | 28.2 | 25.85 | 23.5 | 21.15 | 18.8 | 16.45 | 14.1 | 11.75 | 9.4 | 7.05 | 4.7 | 2.35 | 0
14 | Remaining Effort [hr]
20 | Number of days in sprint
Reference: Scrum in a Nutshell
Reference: Understanding Burndown Charts
Editable version
Go to [File/Make a Copy] to edit and collaborate with your team
Press [right click/Comment] to include suggestions, comments or questions

## Product Backlog
Story Name | Story Description | Status
Product Backlog | Implement a simple list of features or user stories The PO should be able to sort by priority | To Do
Sprint Backlog | The DT should be able to register the tasks and remaining effort with ease The PO and SM should be able to sort by priority | To Do
Visual Progress | The SM should be able to have an up to date status of the project with a SCRUM board and a Burndown Chart | To Do
Collaborative | Everyone should be able to make modifications at the same time Should be a tool for everyone to track the progress of the different activities | To Do
Dedicated app | Dedicated APP developed from scratch | Not To Do
Support and Help | Create a video and a way of improving this file | To Do
Explanation | Explain how to interpret burndown chart | To Do

## Setup
Product Backlog Status Options | Spring Backlog Status Options | Development Team
Not To Do | To Do | Frank
To Do | Doing | Mary
Done | Done | Daniel
OK

## Change Log
Version | Date | Changes
0.1.0 | 2017-11-06 | Removed the SCRUM board due to lack of usage and redundancy with Sprint Backlog.
0.1.1 | 2017-11-12 | Removed date columns on Sprint Backlog to simplify filling the data. Thus creating a manual step on Visible Progress to update the burndown chart.
0.1.2 | 2017-12-18 | Redacted conditions in readme
0.1.3 | 2017-12-21 | Included an easier way to update the burndown chart and included a FAQ
0.1.3.1 | 2018-01-18 | Fixed inconsistent formats on Sprint Backlog
0.1.4 | 2018-01-29 | Replaced SCRUM info page by a simpler setup page.
0.1.4.1 | 2018-02-01 | Fixed validation error
0.1.4.2 | 2018-02-01 | Included readme on the front
0.1.4.3 | 2018-06-07 | Eliminated unnecessary row on Burndown Chart due to a new version of charts in google spreadsheets
0.1.5 | 2018-09-07 | Removed abbreviations on comments with instructions
0.1.5.1 | 2018-10-07 | Adjusted Burndown Chart with formulas with date (just for display)
0.1.5.2 | 2018-08-15 | Removed the SCRUM editable file to maintain only one file, made notes with instructions on how to make your own copy on each page
0.1.5.3 | 2018-08-15 | Changed the word check out to Pull according to the reference document
0.1.6 | 2018-08-16 | Changed Colors, hidden pages
0.1.6.1 | 2018-08-21 | Added colors to tabs
0.1.6.2 | 2018-10-08 | Updated FAQ
0.1.6.3 | 2019-09-05 | Incuded reference to burndown charts
0.1.6.4 | 2019-10-09 | Changed features to user stories
0.1.7 | 2019-10-10 | References validation to named range

## FAQ
Question | Answer
How do I assign priority to Product Backlog Stories? | By dragging and dropping rows.
How do I assign priority to Sprint Backlog tasks? | By dragging and dropping rows.
How do I setup the burndown chart? | At the beginning of the sprint you setup the dates and adjust the sprint length by extending the sprint and dragging formulas as needed.
Why do the dates of the sprint have a formula? | Just to keep the dates as if the sprint was running, in practice the dates should be static and assigned by your Scrum Master.
How do I update the burndown chart? | Copy every day the "remaining effort" to the row named "Real" and you should see your chart updated.
How do I add features to the sprint backlog or product backlog? | It works better if you just write your task and drag it to the priority needed.
How do I make suggestions to this template? | You can make comments as needed. They will be reviewd and worked on or included here
How do I edit this file? | You can make your own copy with File/ Create a Copy or Download as a File. Also you are free to make comments to improve this file
How is this template made? | There are some simple formulas, data validation and conditional formatting that makes it possible.
How many stories can be added? | There is a limit of 100 sprint backlog and product backlog stories. You can add more if you edit the formulas and data validations.
Why there is no SCRUM board? | The information is very similar to Sprint Backlog, it was removed to have a simpler file and have an emphasis on the Burndown chart.
Why there is no time tracking? | The idea to estimate if the stories will be done by the end of the sprint, which can be done with the trendline on the burndown chart.
How can I add more than 9 development team members? | It's not recommended but you can add a row on the Options sheet and check on the Sprint Backlog if the drop down validation still works.