## BLANK Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Startup project |  | 17 | 17 | 0 |  |  |  |  | 100%
1.1 | System design | Ivan Giacomoni | 5 | 5 | 0 | 1 | 2022-01-10 | 2022-01-11 | 2 | 100% | bar: WEEK 1 M to WEEK 1 T
1.2 | System documentation | Ivan Giacomoni | 2 | 2 | 0 | 1 | 2022-01-11 | 2022-01-12 | 2 | 100% | bar: WEEK 1 T to WEEK 1 W
1.3 | System architecture | Ivan Giacomoni | 3 | 3 | 0 | 1 | 2022-01-12 | 2022-01-13 | 2 | 100% | bar: WEEK 1 W to WEEK 1 R
1.4 | User stories | Ivan Giacomoni | 2 | 2 | 0 | 1 | 2022-01-13 | 2022-01-13 | 1 | 100% | bar: WEEK 1 R
1.5 | Documentation review | Ivan Giacomoni | 2 | 2 | 0 | 1 | 2022-01-13 | 2022-01-14 | 2 | 100% | bar: WEEK 1 R to WEEK 1 F
1.6 | Data modelling | Ivan Giacomoni | 3 | 3 | 0 | 1 | 2022-01-14 | 2022-01-14 | 1 | 100% | bar: WEEK 1 F
2 | Eco Server development |  | 32 | 32 | 0 |  |  |  |  | 100%
2.1 | Chemical agents features | Daniele Bufalieri | 10 | 10 | 0 | 2 | 2022-01-17 | 2022-01-19 | 3 | 100% | bar: WEEK 2 M to WEEK 2 W
2.2 | Authentication features and db connection | Ivan Giacomoni | 8 | 8 | 0 | 2 | 2022-01-17 | 2022-01-19 | 3 | 100% | bar: WEEK 2 M to WEEK 2 W
2.3 | Meteo features and configuration files | Daniele Bufalieri | 4 | 4 | 0 | 2 | 2022-01-19 | 2022-01-20 | 2 | 100% | bar: WEEK 2 W to WEEK 2 R
2.4 | Registration and announcements features | Ivan Giacomoni | 4 | 4 | 0 | 2 | 2022-01-19 | 2022-01-20 | 2 | 100% | bar: WEEK 2 W to WEEK 2 R
2.5 | Helper functionalities and admin features | Daniele Bufalieri | 3 | 3 | 0 | 2 | 2022-01-20 | 2022-01-21 | 2 | 100% | bar: WEEK 2 R to WEEK 2 F
2.6 | Token management for announcements and configuration update | Ivan Giacomoni | 3 | 3 | 0 | 2 | 2022-01-20 | 2022-01-21 | 2 | 100% | bar: WEEK 2 R to WEEK 2 F
3 | Eco threshold and Eco app development |  | 30 | 30 | 0 |  |  |  |  | 100%
3.1 | Bug fixing on Eco-Server | Daniele Bufalieri | 2 | 2 | 0 | 3 | 2022-01-24 | 2022-01-24 | 1 | 100% | bar: WEEK 3 M
3.2 | AMQP Producer | Ivan Giacomoni | 3 | 3 | 0 | 3 | 2022-01-24 | 2022-01-24 | 1 | 100% | bar: WEEK 3 M
3.3 | AMQP Consumer and basic setup | Daniele Bufalieri | 5 | 5 | 0 | 3 | 2022-01-25 | 2022-01-26 | 2 | 100% | bar: WEEK 3 T to WEEK 3 W
3.4 | Email and support features | Ivan Giacomoni | 6 | 6 | 0 | 3 | 2022-01-25 | 2022-01-26 | 2 | 100% | bar: WEEK 3 T to WEEK 3 W
3.5 | Added basic setup Vue | Daniele Bufalieri | 2 | 2 | 0 | 3 | 2022-01-27 | 2022-01-27 | 1 | 100% | bar: WEEK 3 R
3.6 | Added registration and login views | Ivan Giacomoni | 5 | 5 | 0 | 3 | 2022-01-27 | 2022-01-27 | 1 | 100% | bar: WEEK 3 R
3.7 | Added dashboard components and logout | Ivan Giacomoni | 3 | 3 | 0 | 3 | 2022-01-28 | 2022-01-28 | 1 | 100% | bar: WEEK 3 F
3.8 | Added password recovery | Daniele Bufalieri | 4 | 4 | 0 | 3 | 2022-01-28 | 2022-01-28 | 1 | 100% | bar: WEEK 3 F
4 | Eco app development and Documents review
4.1 | Dashboard and change password features and several assets | Daniele Bufalieri | 6 | 6 | 0 | 4 | 2022-01-31 | 2022-02-01 | 2 | 100% | bar: WEEK 4 M to WEEK 4 T
4.2 | Advanced features | Ivan Giacomoni | 8 | 8 | 0 | 4 | 2022-01-31 | 2022-02-01 | 2 | 100% | bar: WEEK 4 M to WEEK 4 T
4.3 | User stories booklet | Ivan Giacomoni | 6 | 6 | 0 | 4 | 2022-02-02 | 2022-02-04 | 3 | 100% | bar: WEEK 4 W to WEEK 4 F
5 | Documents review
5.1 | FP + Cocomo 2 booklet | Daniele Bufalieri | 5 | 5 | 0 | 5 | 2022-02-07 | 2022-02-08 | 2 | 100% | bar: WEEK 5 M to WEEK 5 T
5.2 | Scrum and design booklet | Ivan Giacomoni | 7 | 7 | 0 | 5 | 2022-02-08 | 2022-02-10 | 3 | 100% | bar: WEEK 5 T to WEEK 5 R
5.3 | Slide for presentation | Ivan Giacomoni | 4 | 4 | 0 | 5 | 2022-02-11 | 2022-02-11 | 1 | 100% | bar: WEEK 5 F
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 115 | 115 | 0 | 25 | 4.6 |  |  | DAY | WEEK 1 M: 1; WEEK 1 T: 2; WEEK 1 W: 3; WEEK 1 R: 4; WEEK 1 F: 5; WEEK 2 M: 6; WEEK 2 T: 7; WEEK 2 W: 8; WEEK 2 R: 9; WEEK 2 F: 10; WEEK 3 M: 11; WEEK 3 T: 12; WEEK 3 W: 13; WEEK 3 R: 14; WEEK 3 F: 15; WEEK 4 M: 16; WEEK 4 T: 17; WEEK 4 W: 18; WEEK 4 R: 19; WEEK 4 F: 20; WEEK 5 M: 21; WEEK 5 T: 22; WEEK 5 W: 23; WEEK 5 R: 24; WEEK 5 F: 25; WEEK 6 T: TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | WEEK 1 M: 115; WEEK 1 T: 110.4; WEEK 1 W: 105.8; WEEK 1 R: 101.2; WEEK 1 F: 96.6; WEEK 2 M: 92; WEEK 2 T: 87.4; WEEK 2 W: 82.8; WEEK 2 R: 78.2; WEEK 2 F: 73.6; WEEK 3 M: 69; WEEK 3 T: 64.4; WEEK 3 W: 59.8; WEEK 3 R: 55.2; WEEK 3 F: 50.6; WEEK 4 M: 46; WEEK 4 T: 41.4; WEEK 4 W: 36.8; WEEK 4 R: 32.2; WEEK 4 F: 27.6; WEEK 5 M: 23; WEEK 5 T: 18.4; WEEK 5 W: 13.8; WEEK 5 R: 9.2; WEEK 5 F: 4.6
[10 empty] | ESTIMATE | WEEK 1 M: 115; WEEK 1 T: 112; WEEK 1 W: 108; WEEK 1 R: 105; WEEK 1 F: 103; WEEK 2 M: 98; WEEK 2 T: 92; WEEK 2 W: 86; WEEK 2 R: 78; WEEK 2 F: 72; WEEK 3 M: 66; WEEK 3 T: 61; WEEK 3 W: 55; WEEK 3 R: 50; WEEK 3 F: 43; WEEK 4 M: 36; WEEK 4 T: 28; WEEK 4 W: 22; WEEK 4 R: 20; WEEK 4 F: 18; WEEK 5 M: 16; WEEK 5 T: 13; WEEK 5 W: 9; WEEK 5 R: 7; WEEK 5 F: 4; WEEK 6 T: 115
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | WEEK 1 M: 3; WEEK 1 T: 4; WEEK 1 W: 3; WEEK 1 R: 2; WEEK 1 F: 5; WEEK 2 M: 6; WEEK 2 T: 6; WEEK 2 W: 8; WEEK 2 R: 6; WEEK 2 F: 6; WEEK 3 M: 5; WEEK 3 T: 6; WEEK 3 W: 5; WEEK 3 R: 7; WEEK 3 F: 7; WEEK 4 M: 8; WEEK 4 T: 6; WEEK 4 W: 2; WEEK 4 R: 2; WEEK 4 F: 2; WEEK 5 M: 3; WEEK 5 T: 4; WEEK 5 W: 2; WEEK 5 R: 3; WEEK 5 F: 4; WEEK 6 T: 115
[10 empty] | HRS REMAINING | WEEK 1 M: 112; WEEK 1 T: 108; WEEK 1 W: 105; WEEK 1 R: 103; WEEK 1 F: 98; WEEK 2 M: 92; WEEK 2 T: 86; WEEK 2 W: 78; WEEK 2 R: 72; WEEK 2 F: 66; WEEK 3 M: 61; WEEK 3 T: 55; WEEK 3 W: 50; WEEK 3 R: 43; WEEK 3 F: 36; WEEK 4 M: 28; WEEK 4 T: 22; WEEK 4 W: 20; WEEK 4 R: 18; WEEK 4 F: 16; WEEK 5 M: 13; WEEK 5 T: 9; WEEK 5 W: 7; WEEK 5 R: 4; WEEK 5 F: 0; WEEK 6 T: 0
CLICK HERE TO CREATE SCRUM PROJECT MANAGEMENT GANTT CHART TEMPLATES IN SMARTSHEET